## Introduction
The "Major Project Phase by Count" tab of this workbook provides the percentages of the Great American Outdoors Act (GAOA) National Parks and Public Land Legacy Restoration Fund (LRF) projects across the six major project phases for the full portfolio and for each of the four bureaus. The "Major Project Phase by Budget" tab of this workbook provides the percentages of the estimated GAOA LRF project budget across the six major project phases for the full portfolio and for each of the four bureaus. The information in this workbook is displayed on the Department of the Interior's GAOA LRF website in the 'Percent of GAOA LRF Budget and Project Count by Major Project Phase' visualization, which is an interactive stacked bar chart that allows the user to see the distribution of enacted GAOA LRF projects across the six major project phases: Planning, Design, Procurement, Construction, Substantially Complete, and Complete. The user has the option to view phase distribution "By Project Count" or "By GAOA LRF Budget' and can filter by bureau. The project status data is updated as of December 31, 2025, and the project budget data is updated as of September 30, 2025.
Column Header Descriptions - "Major Project Phase by Count" tab:
Major Project Phase: One of the six major project phases for GAOA LRF projects, that describes the project's current execution status based on the primary construction activities.
Percentage of All GAOA LRF Projects: The total percentage of GAOA LRF projects by count in a given phase across all the four bureaus, rounded to the nearest whole number.
Percentage of Bureau of Indian Education LRF Projects: The percentage of Bureau of Indian Education GAOA LRF projects by count in a given phase, rounded to the nearest whole number.
Percentage of Bureau of Land Management LRF Projects: The percentage of Bureau of Land Management GAOA LRF projects by count in a given phase, rounded to the nearest whole number.
Percentage of National Park Service LRF Projects: The percentage of National Park Service GAOA LRF projects by count in a given phase, rounded to the nearest whole number.
Percentage of U.S. Fish and Wildlife Service LRF Projects: The percentage of U.S. Fish and Wildlife Service GAOA LRF projects by count in a given phase, rounded to the nearest whole number.
Column Header Descriptions - "Major Project Phase by Budget" tab:
Major Project Phase: One of the six major project phases for GAOA LRF projects, that describes the project's current execution status based on the primary construction activities.
Percentage of All GAOA LRF Projects Budget: The total percentage of estimated GAOA LRF project budget in a given phase across all the four bureaus, rounded to the nearest whole number.
Percentage of Bureau of Indian Education LRF Projects Budget: The percentage of Bureau of Indian Education estimated GAOA LRF project budget in a given phase, rounded to the nearest whole number.
Percentage of Bureau of Land Management LRF Projects Budget: The percentage of Bureau of Land Management estimated GAOA LRF project budget in a given phase, rounded to the nearest whole number.
Percentage of National Park Service LRF Projects Budget: The percentage of National Park Service estimated GAOA LRF project budget in a given phase, rounded to the nearest whole number.
Percentage of U.S. Fish and Wildlife Service LRF Projects Budget: The percentage of U.S. Fish and Wildlife Service estimated GAOA LRF project budget in a given phase, rounded to the nearest whole number.

## Major Project Phase by Count
Major Project Phase | Percentage of All LRF Projects | Percentage of Bureau of Indian Education LRF Projects | Percentage of Bureau of Land Management LRF Projects | Percentage of National Park Service LRF Projects | Percentage of U.S. Fish and Wildlife Service LRF Projects
Planning | 16% | 8% | 19% | 15% | 9%
Design | 15% | 17% | 11% | 18% | 18%
Procurement | 7% | 0% | 5% | 10% | 7%
Construction | 30% | 25% | 20% | 33% | 53%
Substantially Complete | 18% | 50% | 20% | 17% | 9%
Complete | 14% | 0% | 25% | 7% | 4%

## Major Project Phase by Budget
Major Project Phase | Percentage of All LRF Projects Budget | Percentage of Bureau of Indian Education LRF Projects Budget | Percentage of Bureau of Land Management LRF Projects Budget | Percentage of National Park Service LRF Projects Budget | Percentage of U.S. Fish and Wildlife Service LRF Projects Budget
Planning | 12% | 1% | 36% | 11% | 20%
Design | 17% | 20% | 20% | 16% | 17%
Procurement | 10% | 0% | 8% | 11% | 6%
Construction | 48% | 73% | 26% | 47% | 51%
Substantially Complete | 11% | 6% | 6% | 13% | 6%
Complete | 2% | 0% | 4% | 2% | 0%